## Sheet1
Task | Start | End | Duration | Status | Completed | Goal/Comments
Initial Plan | 2018-06-20 | 2018-06-21 | 1 | Complete | x
Literature Review | 2018-06-20 | 2018-07-06 | 12 | Ongoing |  | Revise
Github Project Create/Invite | 2018-07-18 | 2018-07-18 | 1 | Complete | x
Updated Milestsones | 2018-07-18 | 2018-07-19 | 1 | Complete | x
Software Downloads | 2018-07-12 |  | 4 | Ongoing |  | Simulator - needs IP Address & Baxter serial number?
Create Blockly Library | 2018-07-10 |  |  | Ongoing |  | Figure out how many moves are required
Testing | 2018-07-23 | 2018-08-03 | 10 | Not Started |  | What measurements will be used? How to quantify?
Results Review | 2018-08-06 | 2018-08-17 | 10 | Not Started |  | Stats?
Writing | 2018-08-20 | 2018-09-14 | 15 | Not Started |  | Draft Review date…